## Sheet 1
Table 1
Description | Evaluation | Likelihood | Impact Level | Responsibility | Response | Control Measures
App not loading | Deployed product may have issues or missing requirements | Low | High | Website developers & Cloud team | Full deployment test to be done. App requirements and Cloud ports and networks to be checked | Have a backup code and server in place
Links not working | When customers click the links they are not redirected | Low | High | Website developers | Testing of links to be carried out. Re-deployment of app | Regular tests set up on Jenkins
Users details leaked | Users details are exposed on app | Low | High | Website developers | Sections of the app to be taken down and security increased | Regular security updates
Payment details are leaked | Users can be potentially subjected to fraud | Low | High | Website developers | Inform the customers that their info has been leaked | Regular security patches installed
App suffers hacking by pshing | Hackers are weakening the app from the inside and stealing users details | Low | High | Website developers | Security and network teams to fix the issue to prevent further attacks | Regular security patches installed
Copywrite infringement on app | Images or write ups on the app are not authentic or cleared for use. Company could be sued. | Low | Medium | Web Designers & content producers | All text and images must be authentic and or purchased for use | Legal team to vet all content going on app
Payment system not working | If the payments are not coming in customers will shop elsewhere losing the company revenue | Low | High | Website developers | Provide an immediate backup solution to reduce the impact | Regular tests by development team and third party payment system providers
Server goes down | Website/App not functioning | Low | High | Cloud team | Contact cloud provider. Switch over to second server | Ensure there is a backup server in place
Log in details not working | Users unable to log into the app | Low | High | Website developers | Developers need to reset and fix the issue | Regular security patches installed